## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Researching about the tablet features |  | 2
Compare tablet pricing |  | 1
Checking the compatibility of the operating system |  | 1
Getting the quotes for tablets from vendors |  | 2
Milestone: Selection of the vendor based on the quotes |  | 1
Create contracts and statements of work for vendor |  | 1
Delivery of the tablets |  | 10 | 8 | 10 | 21 | M
Installation of the tablets |  | 3
Schedule an electrician |  | 1
Wiring the tables |  | 4 | 2 | 4 | 6 | H
Create a procedure for securing tablets during the closure of restaurant |  | 1
Milestone : Complete a basic test run of the tablet and wiring system |  | 1
Choose a vendor and a package for the customization |  | 2
Convey the package and vendor information to the marketing team |  | 1
Collect information regarding the menu and coupons |  | 10 | 7 | 10 | 15 | M
Complete the customization |  | 2
Integrate tablets with POS software |  | 1 | 0.5 | 1 | 3 | L
Create messaging about payment portal security to display on the tablets |  | 1
Implement a post-dining survey to assess customer satisfaction |  | 1
Milestone: Complete a full test run of the system and its features |  | 1
Preparation for training the managers and waitstaff |  | 10 | 7 | 10 | 15 | H
Include payment security talking points in waitstaff training |  | -
Fix a training schedule date at both the restaurant locations |  | -
First training of the managers about the new system |  | 1 | 0.5 | 1 | 2 | H
Second in-house training of all the staff conducted by managers |  | 1 | 0.5 | 1 | 2 | H
Milestone: Complete training and handing over the system to the restaurant |  | 1

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Possible tasks for launching a tabletop restaurant project | https://www.linkedin.com/pulse/possible-tasks-launching-tabletop-tablet-restaurant-project-irodinjo/
Implementing a tablet POS solution | https://www.touchdynamic.com/wp-content/uploads/2017/05/TD_Tablet-POS-Solution_ebook-7.pdf
How to train restaurant staff to adapt new technology | https://sevenrooms.com/en/blog/how-to-train-restaurant-staff-to-adopt-new-technology/